## Initial Stage
Risk Assessment (Initial Stage)
Aditya Raj - SQL Test Automation Project
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Not meeting submission deadlines | An increased workload due to not meeting project submission deadlines. | 80% | 9 | 7.2 | Breakdown tasks and get them done within a manageable timeframe before the submission deadline so that work is submitted on time. | Work harder to catching up to where I'm supposed to be at with project work. | When the workload is getting harder to manage.
5 | COVID-19 Alert Level change | Change to COVID-19 Alert Level 3 or 4, unable to work on project at Ara, will have to work from home. | 15% | 7 | 1.05 | Be prepared to work from home, keep all documents on OneDrive and other places for easy access from anywhere. | Work from home, use the OneDrive pre-saved work to continue project from home. | When government instructions are announced and/or have become active.
2 | Sickness | Work deadline delays due to sickness (fever, weakness, cold) | 20% | 5 | 1 | Stay safe and healthy, keep warm, social distance, wash hands regularly, wear a mask in public. | Take medication on time and stay home. Get rest and eat healthy. Keep warm. Contact doctor to get tested. | When I get sick, feel weak and/or have symptoms of sickness.
3 | Data loss/ corruption | Data lost due to accidental deletion or corruption or damage of hardware | 10% | 9 | 0.9 | Have many copies of files backed up on OneDrive and locally on an external hard drive or home desktop/laptop. Also keep many version to revert back to if needed. | Use backup data from wherever available. | When some or all data is lost.
4 | Major earthquake | Damage to home and workplace, unable to access work on project. Possibly not internet or electricity. | 5% | 9 | 0.45 | Keep all documents on OneDrive and other places for easy access from anywhere. | Continue working from where possible. | Whenever its safe to do so after the earthquake.

## Mid Stage
Risk Assessment (Mid Stage)
Aditya Raj - SQL Test Automation Project
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Not meeting submission deadlines | An increased workload due to not meeting project submission deadlines. | 90% | 9 | 8.1 | Breakdown tasks and get them done within a manageable timeframe before the submission deadline so that work is submitted on time. | Work harder to catching up to where I'm supposed to be at with project work. | When the workload is getting harder to manage.
2 | Sickness | Work deadline delays due to sickness (fever, weakness, cold) | 30% | 6 | 1.8 | Stay safe and healthy, keep warm, social distance, wash hands regularly, wear a mask in public. | Take medication on time and stay home. Get rest and eat healthy. Keep warm. Contact doctor to get tested. | When I get sick, feel weak and/or have symptoms of sickness.
3 | Data loss/ corruption | Data lost due to accidental deletion or corruption or damage of hardware | 10% | 9 | 0.9 | Have many copies of files backed up on OneDrive and locally on an external hard drive or home desktop/laptop. Also keep many version to revert back to if needed. | Use backup data from wherever available. | When some or all data is lost.
4 | Major earthquake | Damage to home and workplace, unable to access work on project. Possibly not internet or electricity. | 5% | 9 | 0.45 | Keep all documents on OneDrive and other places for easy access from anywhere. | Continue working from where possible. | Whenever its safe to do so after the earthquake.
5 | COVID-19 Alert Level change | Change to COVID-19 Alert Level 3 or 4, unable to work on project at Ara, will have to work from home. | 5% | 5 | 0.25 | Be prepared to work from home, keep all documents on OneDrive and other places for easy access from anywhere. | Work from home, use the OneDrive pre-saved work to continue project from home. | When government instructions are announced and/or have become active.

## Final Stage
Risk Assessment (Final Stage)
Aditya Raj - SQL Test Automation Project
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Not meeting submission deadlines | An increased workload due to not meeting project submission deadlines. | 90% | 9 | 8.1 | Breakdown tasks and get them done within a manageable timeframe before the submission deadline so that work is submitted on time. | Work harder to catching up to where I'm supposed to be at with project work. | When the workload is getting harder to manage.
2 | Sickness | Work deadline delays due to sickness (fever, weakness, cold) | 80% | 6 | 4.8 | Stay safe and healthy, keep warm, social distance, wash hands regularly, wear a mask in public. | Take medication on time and stay home. Get rest and eat healthy. Keep warm. Contact doctor to get tested. | When I get sick, feel weak and/or have symptoms of sickness.
3 | Data loss/ corruption | Data lost due to accidental deletion or corruption or damage of hardware | 10% | 9 | 0.9 | Have many copies of files backed up on OneDrive and locally on an external hard drive or home desktop/laptop. Also keep many version to revert back to if needed. | Use backup data from wherever available. | When some or all data is lost.
4 | Major earthquake | Damage to home and workplace, unable to access work on project. Possibly not internet or electricity. | 5% | 9 | 0.45 | Keep all documents on OneDrive and other places for easy access from anywhere. | Continue working from where possible. | Whenever its safe to do so after the earthquake.
5 | COVID-19 Alert Level change | Change to COVID-19 Alert Level 3 or 4, unable to work on project at Ara, will have to work from home. | 3% | 3 | 0.09 | Be prepared to work from home, keep all documents on OneDrive and other places for easy access from anywhere. | Work from home, use the OneDrive pre-saved work to continue project from home. | When government instructions are announced and/or have become active.