## Sprint Backlog
Sprint/Product Backlog
Sprint # | Sprint Outcome | Start Date | End Date | Status
1 | Learning SQL Server and Testing tSQLt Framework. | 2021-04-12 | 2021-04-15 | Done
2 | Create Correct and Incorrect Answer Testing Scripts for Single Question and Query - tSQLt | 2021-04-16 | 2021-04-28 | Done
3 | Create Correct and Incorrect Answer Testing Scripts for Multiple Questions and Queries - tSQLt | 2021-04-29 | 2021-05-12 | Done
4 | Use Restored NORTHWND Database. Create Testing Script using Real Course Tests - tSQLt | 2021-05-13 | 2021-05-26 | Done
5 | Create First Packaged Prototype Program using C# .NET Framework - Test Multiple Queries for One Student, Use Real Course Tests. | 2021-05-26 | 2021-06-03 | Done
6 | Create Second Packaged Prototype Program using C# .NET Framework - Test Multiple Queries for Multiple Students, Use Real Course Tests with Real Student Answers. | 2021-06-04 | 2021-06-11 | Done
7 | Create Final Portable Packaged Prototype Program using C# .NET Framework - Test Program with Second Set of Real Course Tests and Real Student Answers. Create Product Manual Documentation. | 2021-06-11 | 2021-06-18 | Done
Completion | Packed Program Ready for Deployment. Create Video Product Documentation. | 2021-06-19 | - | In Progress

## Sprint #1
Task Planning - Sprint #1
Task | Task Status | Completion Date
Look at how tSQLt Compare Table works | Done | 2021-04-15
Get/Make a sample database | Done | 2021-04-15
Do a join query - All orders with Customer Name | Done | 2021-04-15
Use join query as correct answer | Not Started | Next Sprint
Make test with different order fields, sorted differently | Done | 2021-04-15
Make test with fields missing | Done | 2021-04-15
Make test with spelling mistakes | Done | 2021-04-15
Make test with case sensibility issues | Not Started | Next Sprint
Make all code work with SQL Server 2019 | Not Started | Next Sprint
Upload all code to GitHub repo | Done | 2021-04-15

## Sprint #2
Task Planning - Sprint #2
Task | Task Status | Completion Date
Use join query as correct answer | Done | 2021-04-19
Make test with case sensibility issues | Done | 2021-04-19
Create script with correct answer queries | Done | 2021-04-27
Create testing script to test the correct answer queries | Done | 2021-04-27
Create script with wrong answer queries | Done | 2021-04-27
Create testing script to test the wrong answer queries | Done | 2021-04-27
Make all code work with SQL Server 2019 | Done | 2021-04-27
Upload all code to GitHub repo | Done | 2021-04-27

## Sprint #3
Task Planning - Sprint #3
Task | Task Status | Completion Date
Create database to work with correct answer queries | Done | 2021-05-11
Create correct answer queries script | Done | 2021-05-11
Create database to work with incorrect answer queries | Done | 2021-05-11
Create incorrect answer queries script | Done | 2021-05-11
Create single testing script to test correct and incorrect queries | Done | 2021-05-12
Reduce the use of hard code | Done | 2021-05-12
Upload all code to GitHub repo | Done | 2021-05-12

## Sprint #4
Task Planning - Sprint #4
Task | Task Status | Completion Date
Restore NORTHWND database to SSMS | Done | 2021-05-15
Create model answer script for MyLunchTest | Done | 2021-05-20
Create testing script for MyLunchTest | Done | 2021-05-20
Create correct query answers testing script for MyLunchTest | Done | 2021-05-20
Create incorrect query answers testing script for MyLunchTest | Done | 2021-05-20
Test MyLunchTest with SQL Server 2017 and 2019 | Done | 2021-05-20
Create model answer script for SQLPracticalTest | Done | 2021-05-25
Create testing script for SQLPracticalTest | Done | 2021-05-25
Create correct query answers testing script for SQLPracticalTest | Done | 2021-05-25
Create incorrect query answers testing script for SQLPracticalTest | Done | 2021-05-25
Test SQLPracticalTest with SQL Server 2017 and 2019 | Done | 2021-05-25
Upload all code to GitHub repo | Done | 2021-05-25

## Sprint #5
Task Planning - Sprint #5
Task | Task Status | Completion Date
Create Visual Studio 2019 Project Solution | Done | 2021-05-27
Automatically connect to SQL Server and database | Done | 2021-05-29
Automatically setup tSQLt | Done | 2021-05-29
Automatically setup model answer | Done | 2021-05-29
Add ability to upload student answer script | Done | 2021-05-29
Get student results with Mark Test button | Done | 2021-05-29
Present text results in text box in program | Done | 2021-06-02
Test program using sample student scripts (50%, 95%, 100%) | Done | 2021-06-02
Upload all code to GitHub repo | Done | 2021-06-03

## Sprint #6
Task Planning - Sprint #6
Task | Task Status | Completion Date
Make copy of previous Visual Studio project solution | Done | 2021-06-07
Ability to connect to SQL Server and database + auto install tSQLt | Done | 2021-06-07
Model answer script uploader | Done | 2021-06-07
tSQLt testing script uploader | Done | 2021-06-07
Bulk student answer directory uploader | Done | 2021-06-08
Loop execute each SQL file, testing script and output results to TXT file | Done | 2021-06-08
Provide list of output files | Done | 2021-06-08
Show output folder button, open in file explorer | Done | 2021-06-09
Order questions in order of test questions | Done | 2021-06-09
Use real life practical test answers to test program | Done | 2021-06-09
Upload all code to GitHub repo | Done | 2021-06-10

## Sprint #7
Task Planning - Sprint #7
Task | Task Status | Completion Date
Packaged product with setup wizard | Done | 2021-06-14
Bug fix: show directory with error | Done | 2021-06-14
Bug fix: execute tSQLt testing script before running | Done | 2021-06-14
Test program with second set of real life practical test answers | Done | 2021-06-14
Write template scripts for users - testing, model and student answer scripts | Done | 2021-06-14
Write product manual documentation (word document) | Done | 2021-06-17
Package program as portable executable | Done | 2021-06-17

## Completion
Task Planning - Completion
Task | Task Status | Completion Date
Packed program ready for deployment. | Done | 2021-06-25
Create video product documentation with text captions | Done | 2021-06-27